## Sheet1
Status Update 1 | 2022-08-25 | 2022-09-08 | 2022-09-22 | 2022-10-06 | 2022-10-20 | 2022-11-03 | 2022-11-16 | 2022-12-01
Power Supply Retest, Adjusted Parts Order | bar: 2022-08-25 to 2022-09-08
Notifications | 2022-11-03: Catch Up
Glucose Input System | 2022-11-03: In Progress
Dispenser Control Circuit Redesign | 2022-11-03: Finished
Source parts for Stock Checker | 2022-11-03: Not Started
Status Update 2
Power system testing | bar: 2022-09-08
Casing Initial Design in AutoCadd | bar: 2022-09-08 to 2022-09-22
BMI Information implementation | bar: 2022-09-22
Breadboard MOSFETs and test | bar: 2022-09-22
Test Sensors and redesign Code | bar: 2022-09-22 to 2022-10-06
Help Kelton with Nextion for usability feedback | bar: 2022-09-22 to 2022-10-06
Status Update 3
Complete Integration with microcontroller | bar: 2022-09-22 to 2022-10-20
Casing 3D Print submission | bar: 2022-09-22 to 2022-10-20
design PCB for Dispenser MCU and control | bar: 2022-10-06 to 2022-10-20
Work with Holden on CAD for housing | bar: 2022-10-06 to 2022-11-03
Backend Setup | bar: 2022-10-06 to 2022-11-03
Nextion Display UX Design | bar: 2022-10-06 to 2022-11-03
Status Update 4
Case loading and Complete Integration | bar: 2022-11-03 to 2022-11-16
Printing and Installing sensors and stock checker | bar: 2022-11-03 to 2022-11-16
PCB install/test | bar: 2022-11-03 to 2022-11-16
Nextion Display UX Implementation | bar: 2022-10-20 to 2022-11-03
Application cleanup and finalization | bar: 2022-10-20 to 2022-11-16
Status Update 5
Final Testing and Demo Prep | bar: 2022-11-03 to 2022-11-16
Final Presentation | bar: 2022-11-16
Final Demo | bar: 2022-12-01